## Flu vaccine
Steps to Implement Required Flu Vaccination for Health Care Workers
Step No. | WHAT TO DO | WHEN TO DO | WHO IS ASSIGNED TASK-RESPONSIBLE
POLICY
1 | Form Internal multidisciplinary Implementation team (Infection Prevention, Human Resources, Occupational Health, Communications, Pharmacy , Supply Chain, Legal, Information systems, Regulatory Compliance, medical staff leadership, nursing leadership, etc. ) | Q4 2011
2 | Demonstrate commitment from senior leaders by distributing the CEO/CMO letter | Q4 2011
3 | Develop the phrase that clearly defines the expectation. Ex: “First do no harm; get a Flu shot" or "Flu Fighters" | Q1 2012
4 | Discuss and address Union contract implications and considerations. | Q1 2012
5 | Discuss and address student and resident contracts with Medical, Nursing and Pharmacy Schools to include data tracking, bylaw changes, credentialing | Q1 2012
6 | Discuss and address contracts with Vendors who have vendor representatives in the facility | Q1 2012
7 | Discuss and address medical staff impact for owned and non-owned practices | Q1 2012
8 | Validate Infection Control work practices (masking, hand hygiene, screening visitors, early identification and isolation of patients) | Q1 2012
9 | Determine solutions for those who do not comply with policy (disciplinary action process, alternative job during Flu season, LOA, suspension of medical staff privileges etc). Prepare the appropriate staff leaders to follow up on any violations in a fair and consistent way. | Q1 2012
PROCESS
10 | Define Vendor ordering process for 2012-13 Flu season to include 1) vaccine supply and vendors, 2) ordering process and deadlines, 3) additional stockpile needed to vaccinate workforce, 4) additional supplies needed (syringes, needles, bandages, antiseptics) | Jan 2012
11 | Develop/revise Flu Vaccination Consent Form (see attached example) | Q1 2012
12 | Develop a process to review requests for Flu vaccination staff exemptions. See attached egg allergy decision diagram and CDC vaccine information sheet (VIS). | Q1 2012
13 | Determine workforce access to the vaccine (free vaccine, charge for vaccine, Mobile Stations, extended hours in employee health, etc) | Q2 2012
Measurement
14 | Develop a process to enter workforce vaccine information/data into a database | Q2 2012
15 | Develop data reports to monitor and communicate progress (# vaccinations and # approved exemptions by job group, reasons for exemptions, total population eligible to receive vaccine, etc) | Q2 2012
Communication & Education
16 | Establish a dedicated Flu Vaccine email address for questions and answers | Q2 2012
17 | Arrange to place all final materials on intranet site (presentations, newsletters, vaccine rates, forms, etc) | Q2 2012
18 | Develop education plan to include (see example educational PowerPoint's): | Q2 2012
a. principles and goals
b. list of workforce questions with answers
c. Flu policy and access to vaccine
d. Dispelling any myths about vaccine safety and efficacy
19 | Educate senior and operational leaders about the policy | Q3 2012
20 | Provide leaders with a script to assure the message about the policy stresses patient safety. (See FAQ's) | Q3 2012
21 | Integrate the Flu Vaccine message into all meetings and discussions. | Q3 2012
22 | Educate the workforce staff about the policy | Q3 2012
23 | Educate all physicians about the policy | Q3 2012
24 | Educate the Board of Directors about the policy | Q3 2012
Evaluation & Recognition
25 | Consider fun activities to engage both leaders and staff during the implementation phase. Suggestions: poster contest, coaching cards, crossword puzzle with prizes for submitting the answers, reminders on computer screens, red handouts (pens, rulers, etc.) | Q3 2012
26 | Begin to develop data and generate reports to demonstrate and show progress on implementation phase | Q4 2012
27 | The intranet site is updated with Flu vaccine forms, newsletters, presentations, and success stories as the policy is being implemented | Q4 2012
28 | Ask leaders to conduct regular “pulse checks” to show leaders’ engagement. | Q4 2012
29 | Visit and recognize staff cited in safety success stories. | Q4 2012
30 | Find and fix problems that make it hard for the workforce to comply with policy | Q4 2012
31 | Check monthly to assure Implementation Team is on track with Implementation plan and timeline | Q4 2012
32 | Prepare for an implementation celebration with the emphasis on thanking all who have worked so hard to reduce hospital acquired flu and improve vaccination rates | Q1 2013